## Project dashboard (hidden)
Understand Requirements
Build the Payroll System
Test the System
Document and Train
OVERALL PROGRESS
Project plan's progress for an end-to-end inventory and payroll system to manage MotorPH products, employee details, and salary.
Total cost
Estimated cost with
contingency is
Total hours
Actual vs. Target Hours
The MotorPh Payroll System Implementation project intends to streamline and automate payroll operations at MotorPh. The system is intended to improve productivity, accuracy, and compliance in employee compensation management while also providing a user-friendly interface for both administrators and employees.

## Project plan
MAIN | TASK/ACTION | STATUS | Planned Start | Planned End | Actual Start | Actual End | REMARKS
Understand Requirements | Gather requirements from HR and finance teams. | Completed
| Document what the payroll system needs to do. | Completed
| Break down work into manageable tasks. | In progress
| Estimate time needed for each task. | In progress
| Assign tasks to team members. | Completed
Build the Payroll System | Develop user authentication and authorization. | In progress
| Create algorithms for salary calculations. | In progress
| Build an easy-to-use data input interface. | Not started
| Add reporting features. | In progress
Test the System | Check each part of the system individually. | In progress
| Test how everything works together. | Not started
| Let users try the system and get feedback. | In progress
Document and Train | Document how the system works. | Not started
| Create user manuals. | In progress
| Train HR and finance staff. | In progress
Deploy the System | Put the system into the live (production) environment. | Not started

## Effort estimate
Tasks | Rate | Hours | Contigency Factor (%) | Total Estimated Cost (Without Contingency) | Total Estimated Cost (With Contingency)
Understand Requirements: |  | 11 | 10% | 210 | 231
Gather requirements from HR and finance teams.
Employee data | 20 | 2 |  | 40
SSS deduction | 20 | 2 |  | 40
Pag-Ibig deduction | 20 | 2 |  | 40
Philhealth deduction | 20 | 2 |  | 40
Witholding tax | 20 | 2 |  | 40
Document what the payroll system needs to do. | 10 | 1 |  | 10
Build the Payroll System: |  | 30 | 25% | 1500 | 1875
Develop user authentication and authorization. | 50 | 5 | 5% | 250
Create algorithms for salary calculations. |  |  |  | 0 |  | 200
Number of hours an employee has worked in a week. | 50 | 5 | 5% | 250
Gross weekly salary of an employee based on hours worked. | 50 | 5 | 5% | 250
Net weekly salary of an employee after applying generic deductions. | 50 | 5 | 5% | 250
Build an easy-to-use data input interface. | 50 | 5 |  | 250
Add reporting features. | 50 | 5 | 5% | 250
Test the System: |  | 15 | 15% | 300 | 345
Check each part of the system individually. | 20 | 5 |  | 100
Test how everything works together. | 20 | 5 |  | 100
Let users try the system and get feedback. | 20 | 5 |  | 100
Document and Train: |  | 11 | 10% | 670 | 737
Document how the system works. | 40 | 3 |  | 120
Create user manuals. | 50 | 5 |  | 250
Train HR and finance staff. | 100 | 3 | 10% | 300
Deploy the System |  | 1 |  | 500 | 500
Put the system into the live (production) environment. | 500 | 1 |  | 500
Post-Implementation Support: |  | 3
Address any issues reported by users post-implementation. |  | 3
Total: |  | 71 |  | 3180 | 3688
Assumptions

## Data (hidden)
MAIN | TASK/ACTION | TARGET | STATUS
Understand Requirements | Gather requirements from HR and finance teams. | 2 | 2 |  | 0 | Not started |  | Hours | Cost w/o | Cost w/
Understand Requirements | Document what the payroll system needs to do. | 2 | 2 |  | 1 | In progress | Understand Requirements: | 11 | 210 | 231
Understand Requirements | Break down work into manageable tasks. | 2 | 1 |  | 2 | Completed | Build the Payroll System: | 30 | 1500 | 1875
Understand Requirements | Estimate time needed for each task. | 2 | 1 |  | -1 | Delayed | Test the System: | 15 | 300 | 345
Understand Requirements | Assign tasks to team members. | 2 | 2 |  |  |  | Document and Train: | 11 | 670 | 737
Build the Payroll System | Develop user authentication and authorization. | 2 | 1 |  |  |  | Deploy the System | 1 | 500 | 500
Build the Payroll System | Create algorithms for salary calculations. | 2 | 1 |  |  |  | Post-Implementation Support: | 3
Build the Payroll System | Build an easy-to-use data input interface. | 2 | 0 |  |  |  |  | 71 | 3180 | 3688
Build the Payroll System | Add reporting features. | 2 | 1
Test the System | Check each part of the system individually. | 2 | 1 | [5 empty] | target | actual
Test the System | Test how everything works together. | 2 | 0 |  |  |  | Understand Requirements | Gather requirements from HR and finance teams. | 3 | 2
Test the System | Let users try the system and get feedback. | 2 | 1 |  |  |  | Understand Requirements | Document what the payroll system needs to do. | 3 | 3
Document and Train | Document how the system works. | 2 | 0 |  |  |  | Understand Requirements | Break down work into manageable tasks. | 3 | 1
Document and Train | Create user manuals. | 2 | 1 |  |  |  | Understand Requirements | Estimate time needed for each task. | 3 | 2
Document and Train | Train HR and finance staff. | 2 | 1 |  |  |  | Understand Requirements | Assign tasks to team members. | 3 | 2
Deploy the System | Put the system into the live (production) environment. | 2 | 0 |  |  |  | Build the Payroll System | Develop user authentication and authorization. | 5 | 3
[7 empty] | Build the Payroll System | Create algorithms for salary calculations. | 5 | 4
[7 empty] | Build the Payroll System | Build an easy-to-use data input interface. | 5 | 4
Understand Requirements | 2 | 6 | 8 | 10 |  |  | Build the Payroll System | Add reporting features. | 5 | 5
Build the Payroll System | 3 | 0 | 3 | 8 |  |  | Test the System | Check each part of the system individually. | 4 | 1
Test the System | 2 | 0 | 2 | 6 |  |  | Test the System | Test how everything works together. | 4 | 1
Document and Train | 2 | 0 | 2 | 6 |  |  | Test the System | Let users try the system and get feedback. | 4 | 2
[7 empty] | Document and Train | Document how the system works. | 3 | 2
Understand Requirements | 80% | 20% | 1 |  |  |  | Document and Train | Create user manuals. | 3 | 1
Build the Payroll System | 37.5% | 62.5% | 1 |  |  |  | Document and Train | Train HR and finance staff. | 3 | 3
Test the System | 33.33% | 66.67% | 1 |  |  |  | Deploy the System | Put the system into the live (production) environment. | 1 | 1
Document and Train | 33.33% | 66.67% | 1
Overall | 46.04%